## Sheet1
# | Task | Description | Estimated Days | Due Date
1 | Analyze data | Look at the images, dimensions, data type, classes, distribution | 2 | 28/11/2020
2 | Pre-process and clean data | Normalization, resizing or any other preprocessing od the images | 1 | 30/11/2020
3 | Augment data for imbalanced classes | Generate synthetic images for classes with few training samples | 2 | 2020-01-12
4 | Create first model using CNN for multi classification | Decide on network layers, activation and loss functions, hyperparameters | 3 | 2020-04-12
5 | Choose metric for evaluating model performance | Accuracy, Precision, Loss, etc.? | 1 | 2020-05-12
6 | Explore transfer learning using pre-trained models on the dataset | Evaluate InceptionV3, ResNet50 and retrain last layers to improve performance | 3 | 2020-08-12
7 | Build and deploy a Flask application | Use the hold-out imager set to showcase the results in a deployed web application | 3 | 2020-11-12